## Handout 6 - Conference TRACKING
Handout 6 - Event/Conference Plan | [34 empty] | As at Australia Day | [6 empty] | The conference
Tracking Calendar
|  | July |  |  |  |  | August |  |  |  |  | September |  |  |  |  | October |  |  |  |  | November |  |  |  |  | December |  |  |  |  | January |  |  |  |  | February |  |  |  | March |  |  |  |  | April |  |  |  |  | May |  |  |  |  | June |  |  |  |  | July |  |  |  |  | August |  |  |  |  | September |  |  |  |  | October
|  | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk1 | Wk2 | Wk3 | Wk4 | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk1 | Wk2 | Wk3 | Wk4 | Wk5
Overall Management
Estimate key parameters (size, budget, funding) | bar: July Wk1 to July Wk2; January Wk4
Agree Dates | bar: July Wk1 to July Wk2; January Wk4
Agree venue(s) | bar: July Wk1 to July Wk2; January Wk4
Conference theme | bar: July Wk1 to July Wk5; January Wk4
Conference branding, logo & designs | bar: July Wk1 to August Wk5; January Wk4
Monthly reporting and monitoring | bar: August Wk1 to August Wk2; September Wk1 to September Wk2; October Wk1 to October Wk2; November Wk1 to November Wk2; December Wk1 to December Wk2; January Wk1 to January Wk2; January Wk4; February Wk1 to February Wk2; March Wk1 to March Wk2
Post Implementation Review | bar: March Wk1 to March Wk5
The Venue(s)
Seek quote to confirm availability | bar: July Wk1 to July Wk5; January Wk4
Book the venue | bar: August Wk1 to September Wk2; January Wk4
Site plan, venue layout | bar: November Wk1 to December Wk5; January Wk4
Equipment, AV, security details | bar: November Wk1 to December Wk5; January Wk4
Catering requirements | bar: January Wk1 to February Wk4
Walkthrough | bar: February Wk1 to March Wk1
Proceedings, speakers and conference papers
Conference structure and running sheet | bar: July Wk1 to July Wk5; January Wk4
Identify Guest speakers & MC | bar: July Wk1 to July Wk5; January Wk4
Briefs for papers and speaker outlines | bar: July Wk5 to August Wk3; January Wk4
Speaker and MC bio's, outlines and photos | bar: August Wk4 to September Wk3; January Wk4
Travel and accommodation arrangements | bar: September Wk4 to December Wk5; January Wk4
Conference papers and presentations | bar: January Wk1 to February Wk4
Program and detailed running schedule | bar: February Wk4
Walkthrough | bar: February Wk1 to March Wk1
Follow up and thankyou | bar: March Wk1 to March Wk5
Marketing, promotion & printing
Conference campaign design and launch | bar: August Wk1 to September Wk5; January Wk4
Conference website | bar: August Wk1 to March Wk5
Style guide established all documents | bar: October Wk1 to November Wk5; January Wk4
Banners and signage | bar: January Wk1 to February Wk4
Attendee bags and lanyards | bar: February Wk1 to March Wk2
Newsletter/website update | bar: October Wk1 to March Wk5
Functions
First night dinner venue and menu | bar: August Wk1 to August Wk5; January Wk4
Special guests identified and invited | bar: October Wk1 to October Wk5; January Wk4
Additional entertainment | bar: November Wk1 to December Wk5; January Wk4
Second night dinner venue and menu | bar: August Wk1 to August Wk5; January Wk4
Special guests identified and invited | bar: October Wk1 to October Wk5; January Wk4
Additional entertainment | bar: November Wk1 to December Wk5; January Wk4
Project management & governance
Funding model approved
Monthly reporting and monitoring
Legend
Preparation and Research |  | January Wk4: ✔; February Wk1: Milestone achieved
Draft versions |  | January Wk4: ✔; February Wk1: On track to deliver
Approval required |  | January Wk4: X; February Wk1: Milestone not achieved on time
Milestone (completed) |  | January Wk4: X; February Wk1: Not on track to deliver

## Handout 7 - Finance report
Handout 7: Conference Finance Report
Cost Centre: 999 - Road Safety Conference
|  |  |  | Month ending December 20XX |  |  | Month ending December 20XX | [5 empty] | Forecast at Completion
|  | Annual | Opening | MTD | MTD | MTD | YTD | YTD | YTD | Annual | Annual Revised | Closing
|  | Budget | Balance | Budget | Actual | Variance | Budget | Actuals | Variance | Budget | Budget | Balance | Budget | Projected | Variance
Revenue
6XXX - exhibitors |  | 15000 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 15000 | 15000 | 15000 | 0
6XXX - sponsorship |  | 150000 |  | 0 | 0 | 0 | 75000 | 0 | -75000 |  |  | 150000 | 150000 | 150000 | 0
6XXX - grants |  | 150000 |  | 0 | 0 | 0 | 75000 | 0 | -75000 |  |  | 150000 | 150000 | 150000 | 0
6XXX - registration |  | 135225.7692 |  | 54090.3077 | 80000 | 25909.6923 | 54090.3077 | 80000 | 25909.6923 |  |  | 55225.7692 | 135225.7692 | 160000 | 24774.2308
Total: Revenue |  | 450225.7692 |  | 54090.3077 | 80000 | 25909.6923 | 204090.3077 | 80000 | -124090.3077 |  |  | 370225.7692 | 450225.7692 | 475000 | 24774.2308
|  | Annual | Opening | MTD | MTD | MTD | YTD | YTD | YTD | Annual | Annual Revised | Closing | Forecast at Completion
|  | Budget | Balance | Budget | Actual | Variance | Budget | Actuals | Variance | Budget | Budget | Balance | Budget | Projected | Variance
Salary and Wages Expenses
7150 - Salaries |  | 54798.8166 | 307021.6327 | 4792.8994 | 4711.1 | 81.7994 | 28437.8698 | 28266.6 | 171.2698 |  | 54798.8166 | 26532.2166 | 54798.8166 | 55000 | -201.1834
7155 - Allowances |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Total: Salary expenses |  | 54798.8166 | 307021.6327 | 4792.8994 | 4711.1 | 81.7994 | 28437.8698 | 28266.6 | 171.2698 |  | 54798.8166 | 26532.2166 | 54798.8166 | 55000 | -201.1834
ONCOST EXPENSES
7201 - Annual leave |  | 4566.568 | 25176.0256 | 399.4083 | 362.3923 | 37.016 | 2369.8225 | 2355.55 | 14.2725 |  | 4566.568 | 2211.018 | 4566.568 | 4583.3333 | -16.7653
7211 - Long Service Leave |  | 2968.2692 | 13091.5333 | 259.6154 | 235.555 | 24.0604 | 1540.3846 | 1531.1075 | 9.2771 |  | 2968.2692 | 1437.1617 | 2968.2692 | 2979.1667 | -10.8974
7220 - Payroll tax |  | 2968.2692 | 18000.8583 | 259.6154 | 235.555 | 24.0604 | 1540.3846 | 1531.1075 | 9.2771 |  | 2968.2692 | 1437.1617 | 2968.2692 | 2979.1667 | -10.8974
7230 - Super |  | 7123.8462 | 29455.95 | 623.0769 | 565.332 | 57.7449 | 3696.9231 | 3674.658 | 22.2651 |  | 7123.8462 | 3449.1882 | 7123.8462 | 7150 | -26.1538
Total: Oncost expenses |  | 17626.9527 | 85724.3673 | 1541.716 | 1398.8343 | 142.8817 | 9147.5148 | 9092.423 | 55.0918 |  | 17626.9527 | 8534.5297 | 17626.9527 | 17691.6667 | -64.714
Total for Employee Expenses |  | 72425.7692 | 392746 | 6334.6154 | 6109.9343 | 224.6811 | 37585.3846 | 37359.023 | 226.3616 |  | 72425.7692 | 35066.7462 | 72425.7692 | 72691.6667 | -265.8974
|  | Annual | Opening | MTD | MTD | MTD | YTD | YTD | YTD | Annual | Annual Revised | Closing | Forecast at Completion
|  | Budget | Balance | Budget | Actual | Variance | Budget | Actuals | Variance | Budget | Budget | Balance | Budget | Projected | Variance
General Operating Expenses
Goods & Services
8820 - Conference Management |  | 45000 | 29075 | 0 | 0 | 0 | 20000 | 20000 | 0 |  | 45000 | 25000 | 45000 | 45000 | 0
8160 - Venue Hire |  | 30000 | 55939 | 0 | 0 | 0 | 15000 | 25000 | -10000 |  | 30000 | 5000 | 30000 | 40000 | -10000
8XXX - Venue AV & exhibits |  | 22000 | 275439 | 0 | 0 | 0 | 0 | 0 | 0 |  | 22000 | 22000 | 22000 | 22000 | 0
8XXX - Accommodation & meals |  | 24000 | 59366 | 0 | 0 | 0 | 0 | 0 | 0 |  | 24000 | 24000 | 24000 | 24000 | 0
8821 - Travel |  | 32000 | 136577 | 32000 | 28675 | 3325 | 32000 | 28765 | 3235 |  | 32000 | 3235 | 32000 | 32000 | 0
8401 - Speaker fees |  | 30000 | 84000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 30000 | 30000 | 30000 | 30000 | 0
8230 - Marketing and printing |  | 65000 | 25924 | 4000 | 3121 | 879 | 39000 | 28301 | 10699 |  | 65000 | 36699 | 65000 | 65000 | 0
8822 - Catering and events |  | 129800 | 16561 | 0 | 0 | 0 | 0 | 0 | 0 |  | 129800 | 129800 | 129800 | 140000 | -10200
8190 - Miscellaneous expenses |  | 0 | 184123 | 0 | 75.3 | -75.3 | 0 | 147.34 | -147.34 |  | 0 | -147.34 | 0 | 147.34 | -147.34
Total for Supplies and Services |  | 377800 | 867004 | 36000 | 31871.3 | 4128.7 | 106000 | 102213.34 | 3786.66 |  | 377800 | 275586.66 | 377800 | 398147.34 | -20347.34
Depreciation
9801 - Depreciation |  | 0 | 83333.34 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Total for Depreciation |  | 0 | 83333.34 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Internal (Dept) Expenditure
8220 - Internal exp - Goods and Services |  | 0 | 16804 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Total for Internal (Dept) Expenditure |  | 0 | 16804 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Total expenses for operating |  | 377800 | 967141.34 | 36000 | 31871.3 | 4128.7 | 106000 | 102213.34 | 3786.66 |  | 377800 | 275586.66 | 377800 | 398147.34 | -20347.34
Total expenses for Project 9999 |  | 450225.7692 | 1359887.34 | 42334.6154 | 37981.2343 | 4353.3811 | 143585.3846 | 139572.363 | 4013.0216 |  | 450225.7692 | 310653.4062 | 450225.7692 | 470839.0067 | -20613.2374
Net result |  | 0 |  | 11755.6923 | 42018.7657 | 30263.0734 | 60504.9231 | -59572.363 | -120077.2861 |  |  | 59572.363 | 0 | 4160.9933 | 4160.9933
|  |  |  | Month |  |  | Inception to date | [5 empty] | Estimate at completion
|  |  |  | Budget | Actual | Variance | Budget | Actual | Variance |  |  |  | Budget | Actual | Variance
|  |  |  | $'000 | $'000 | $'000 | $'000 | $'000 | $'000 |  |  |  | $'000 | $'000 | $'000
Revenue |  |  |  | 54.0903 | 80 | 25.9097 | 204.0903 | 80 | -124.0903 |  |  |  | 450.2258 | 475 | 24.7742
Expenses
| Employee Expenses |  |  | 6.3346 | 6.1099 | 0.22468 | 37.5854 | 37.359 | 0.22636 |  |  |  | 72.4258 | 72.6917 | -0.2659
Goods and Services
| Conference Management |  |  | 0 | 0 | 0 | 20 | 20 | 0 |  |  |  | 45 | 45 | 0
| Venue |  |  | 0 | 0 | 0 | 15 | 25 | -10 |  |  |  | 52 | 62 | -10
| Speakers |  |  | 32 | 28.675 | 3.325 | 32 | 28.765 | 3.235 |  |  |  | 86 | 86 | 0
| Promotions & Printing |  |  | 4 | 3.121 | 0.879 | 39 | 28.301 | 10.699 |  |  |  | 65 | 65 | 0
| Catering and Functions |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 129.8 | 140 | -10.2
| Sundries |  |  | 0 | 0.0753 | -0.0753 | 0 | 0.14734 | -0.14734 |  |  |  | 0 | 0.14734 | -0.14734
Total Expenses |  |  |  | 42.3346 | 37.9812 | 4.3534 | 143.5854 | 139.5724 | 4.013 |  |  |  | 450.2258 | 470.839 | -20.6132
Net result |  |  |  | 11.7557 | 42.0188 | 30.2631 | 60.5049 | -59.5724 | -120.0773 |  |  |  | 0 | 4.161 | 4.161

## Example - Review,Plan TRACKING
Review/Plan schedule |  | Project tracking up to this point
Output (Report or Plan)
|  | Week 1 or Month 1 |  |  |  |  | Week 2 or Month 2 |  |  |  |  | Week 3 or Month 3 |  |  |  |  | Week 4 or Month 4 |  |  |  |  | Week 5 or Month 5 |  |  |  |  | Week 6 or Month 6 |  |  |  |  | Week 7 or Month 7 |  |  |  |  | Week 8 or Month 8 |  |  |  |  | Week 9 or Month 9 |  |  |  |  | Week 10 or Month 10 |  |  |  |  | Week 11 or Month 11 |  |  |  |  | Week 12 or Month 12 |  |  |  |  | Week 1 or Month 1 |  |  |  |  | Week 1 or Month 1 |  |  |  |  | Week 1 or Month 1 |  |  |  |  | Week 1 or Month 1
|  | D/W1 | D/W2 | D/W3 | D/W4 | D/W5 | D/W1 | D/W2 | D/W3 | D/W4 | D/W5 | D/W1 | D/W2 | D/W3 | D/W4 | D/W5 | D/W1 | D/W2 | D/W3 | D/W4 | D/W5 | D/W1 | D/W2 | D/W3 | D/W4 | D/W5 | D/W1 | D/W2 | D/W3 | D/W4 | D/W5 | D/W1 | D/W2 | D/W3 | D/W4 | D/W5 | D/W1 | D/W2 | D/W3 | D/W4 | D/W5 | D/W1 | D/W2 | D/W3 | D/W4 | D/W5 | D/W1 | D/W2 | D/W3 | D/W4 | D/W5 | D/W1 | D/W2 | D/W3 | D/W4 | D/W5 | D/W1 | D/W2 | D/W3 | D/W4 | D/W5 | D/W1 | D/W2 | D/W3 | D/W4 | D/W5 | D/W1 | D/W2 | D/W3 | D/W4 | D/W5 | D/W1 | D/W2 | D/W3 | D/W4 | D/W5 | D/W1 | D/W2 | D/W3 | D/W4 | D/W5
Project Initiation
Terms of Reference | bar: Week 1 or Month 1 D/W1 to Week 1 or Month 1 D/W2; Week 3 or Month 3 D/W4
Outcome Sought & Logic | bar: Week 1 or Month 1 D/W1 to Week 1 or Month 1 D/W2; Week 3 or Month 3 D/W4
Review or Plan parameters and scope established | bar: Week 1 or Month 1 D/W1 to Week 1 or Month 1 D/W2; Week 3 or Month 3 D/W4
Identify data sources & documents | bar: Week 1 or Month 1 D/W1 to Week 1 or Month 1 D/W2; Week 3 or Month 3 D/W4
Identify interviewees and stakeholders | bar: Week 1 or Month 1 D/W1 to Week 1 or Month 1 D/W2; Week 3 or Month 3 D/W4
Identify authors | bar: Week 1 or Month 1 D/W1 to Week 1 or Month 1 D/W2; Week 3 or Month 3 D/W4
Research and Consultation
Initial data gathering and familiarisation | bar: Week 1 or Month 1 D/W3 to Week 2 or Month 2 D/W5; Week 3 or Month 3 D/W4
Data analysis and manipulation | bar: Week 1 or Month 1 D/W3 to Week 3 or Month 3 D/W5
Review existing and historical documents | bar: Week 1 or Month 1 D/W3 to Week 3 or Month 3 D/W5
Conduct interviews or workshops | bar: Week 1 or Month 1 D/W3 to Week 4 or Month 4 D/W3
Second wave research and consultation (after outline report) | bar: Week 6 or Month 6 D/W1 to Week 6 or Month 6 D/W5
Third wave research and consultation (after first draft) | bar: Week 7 or Month 7 D/W4 to Week 7 or Month 7 D/W5
Outline report
Establish report/plan structure and style guide | bar: Week 1 or Month 1 D/W3 to Week 2 or Month 2 D/W5; Week 3 or Month 3 D/W4
Storyboard the narrative | bar: Week 4 or Month 4 D/W4 to Week 5 or Month 5 D/W1
Draft known aspects of the report | bar: Week 5 or Month 5 D/W1 to Week 5 or Month 5 D/W4
Outline report for mid point review - feedback meeting | bar: Week 5 or Month 5 D/W3 to Week 5 or Month 5 D/W5
Drafting process
Follow up from the outline report | bar: Week 6 or Month 6 D/W1 to Week 6 or Month 6 D/W5
First Draft | bar: Week 6 or Month 6 D/W1 to Week 7 or Month 7 D/W3
Edit and review | bar: Week 7 or Month 7 D/W4
Circulate and feedback | bar: Week 7 or Month 7 D/W5
Second draft | bar: Week 7 or Month 7 D/W5 to Week 8 or Month 8 D/W1
Edit and review | bar: Week 8 or Month 8 D/W2 to Week 8 or Month 8 D/W3
Circulate and feedback | bar: Week 8 or Month 8 D/W4
Final document
Final drafting | bar: Week 8 or Month 8 D/W4
Final Edit and review | bar: Week 8 or Month 8 D/W4
Present Final Report | bar: Week 8 or Month 8 D/W5
Internal meetings to present and discuss the report | bar: Week 9 or Month 9 D/W1
Update and publish the final report | bar: Week 9 or Month 9 D/W1 to Week 9 or Month 9 D/W2
Stakeholder consultation on final report | bar: Week 9 or Month 9 D/W3 to Week 9 or Month 9 D/W5
Feedback from stakeholder consultation | bar: Week 10 or Month 10 D/W1 to Week 10 or Month 10 D/W5
Project management & governance
[15 empty] | ✔ |  | Milestone achieved
[15 empty] | ✔ |  | On track to deliver
[15 empty] | X |  | Milestone not achieved on time
[15 empty] | X |  | Not on track to deliver
Legend
Preparation and Research
Draft versions
Approval required
Milestone (completed)